90-DAY AI ADOPTION INITIATIVE

CTIPH Responsible AI Use and Human Verification

DAY 90 OUTCOME CTIPH will have a consistent learner-facing AI-use statement in its D2L courses and a tested disclosure and human-review process for IPE activities.

# SECTION 1 — PROBLEM STATEMENT

CTIPH currently lacks consistent guidance for responsible AI use across its IPE activities, which serve thousands of health sciences students and involve faculty, facilitators, and program partners. Without shared expectations for disclosure, data handling, and human verification, AI-supported work may be applied inconsistently across CTIPH D2L courses.

# SECTION 2 — TARGET AUDIENCE

| Role | AI fluency (1–5) | What they need | Key concern |
| --- | --- | --- | --- |
| CTIPH Director / initiative lead | 4 | A manageable, repeatable process that fits existing D2L and IPE workflows. | Added workload and creation of a process that cannot be sustained. |
| Faculty member, IPE chair, liaison, or collaborator | 2–4 | Clear expectations, examples, and a quick review process. | Accuracy, academic integrity, role confusion, and time required for review. |
| Health sciences students in CTIPH IPE activities | 1–5 | Plain-language rules, a meaningful non-AI option, and a simple way to disclose use. | Unclear permission, unequal access, privacy, or being penalized for misunderstanding expectations. |

# SECTION 3 — AI TOOLS AND APPROACH

| Tool | Modality | Rationale | Data sensitivity | Institutionally approved? |
| --- | --- | --- | --- | --- |
| Verde GenAI | Text-based generative AI for drafting, revising, summarizing, and organizing non-sensitive content. | Provides university-governed access and supports efficient drafting while preserving human judgment and final approval. | Public or Internal only for this initiative. No names, NetIDs, grades, accommodations, survey responses, health information, or other identifiable student data. | Yes — for the Public and Internal data used here, subject to the current UA AI Tools & Data Use Guide. |

Approach: AI may support drafting, editing, organization and strategic planning. CTIPH remains responsible for accuracy, policy alignment, instructional appropriateness, disclosure expectations, and every final decision.

# SECTION 4 — ETHICAL SAFEGUARDS

| Risk | Safeguard mechanism | Responsible party |
| --- | --- | --- |
| Exposure of sensitive or identifiable information | Use only Public or Internal content; exclude student identifiers and restricted or regulated data; confirm data category before entry. | CTIPH Director and every user entering content |
| Inaccurate, fabricated, or misleading content | Verify factual claims, references, links, instructions, and policy statements against authoritative sources before use. | Content author; CTIPH Director gives final approval |
| Unclear or undisclosed AI contribution | Include a standard AI-use statement and a disclosure question whose detail is proportional to the significance of AI’s contribution. | CTIPH Director; students and collaborators disclose their own use |
| AI influencing certification or participation decisions | Require human review whenever AI-supported material is used to verify IPE participation or certification requirements; AI does not make the final decision. | CTIPH Director |
| Workflow does not fit faculty or learner needs | Obtain review from at least one named faculty member, liaison, or collaborator before finalizing the pilot workflow. | CTIPH Director and named reviewer |

# SECTION 5 — EQUITY CONSIDERATIONS

| Population that may benefit less or face higher barriers | Adjustment |
| --- | --- |
| Students without paid tools, reliable technology, or confidence using AI | Do not require AI use. Provide a meaningful non-AI pathway that can meet the same learning and participation requirements without penalty. |
| Students, faculty, or facilitators with limited AI fluency; multilingual learners; or users who need accessible materials | Use plain language and practical examples; explain unfamiliar terms; format materials accessibly; allow questions and clarification without assuming prior AI experience. |

# SECTION 6 — SUCCESS METRICS

| Metric | How measured | Timeline | Minimum acceptable threshold |
| --- | --- | --- | --- |
| Standard AI-use statement completed | Document review against UA guidance and CTIPH needs | By Day 30 | One approved statement ready for D2L use |
| Stakeholder review completed | Email comments, annotated draft, or meeting notes | By Day 60 | Feedback received from at least one named faculty member, liaison, or IPE collaborator |
| CTIPH D2L implementation completed | Director verifies the standard statement is posted in active CTIPH D2L course shells | By Day 90 | Statement present in 100% of active CTIPH-controlled D2L course shells |
| Pilot workflow completed | Disclosure question and human-review checklist are used in, or fully prepared for, one selected IPE activity | By Day 90 | One activity implemented or pilot-ready |
| Guidance is understandable | Brief feedback question plus a log of clarification requests | During or immediately after pilot | At least 80% of respondents rate expectations clear or very clear; no unresolved privacy or permission issue |

# SECTION 7 — ROLLOUT: FIRST THREE STEPS

| Step | What | Who | Resource needed | By when |
| --- | --- | --- | --- | --- |
| 1. Develop | Finalize the CTIPH AI-use statement, disclosure question, and human-review checklist; select the pilot IPE activity and reviewer. | CTIPH Director | Current CTIPH language; AI Champions work; UA AI guidance; D2L access | Day 30 |
| 2. Review | Obtain collaborator feedback, verify alignment with current UA guidance, revise materials, and prepare D2L and pilot content. | CTIPH Director and one faculty member, liaison, or IPE collaborator | Draft materials; reviewer time; UA AI Tools & Data Use Guide | Day 60 |
| 3. Implement and refine | Post the statement in active CTIPH D2L shells; use or prepare the pilot disclosure and review process; record questions and finalize the repeatable workflow. | CTIPH Director; selected activity collaborator as applicable | D2L access; selected worksheet, reflection, or survey item; brief feedback method | Day 90 |

# SECTION 8 — 50-WORD ELEVATOR PITCH

In 90 days, CTIPH will establish consistent, practical expectations for responsible AI use across its interprofessional education courses. We will implement a standard learner-facing statement, pilot one disclosure and human-review process, protect student information, preserve non-AI options, and produce a repeatable workflow that can expand as capacity permits.

Word count: 50

## Initiative Scope and Boundaries

This initiative establishes a focused operational practice, not a campus-wide policy, comprehensive governance framework, research study, or required AI training program. It does not revise every activity-specific component at once. Expansion beyond the initial pilot will depend on results, collaborator input, workload, and capacity.

## Evidence-Grounded Design

The initiative applies the Module 3 workflow practice of identifying the tool, data type, and required human check. It operationalizes the Module 5 work on transparency, accountability, human oversight, equity, and update needs. Current University of Arizona guidance also supports clear instructor expectations, disclosure, appropriate tool selection, and data-sensitive use.

## Core Deliverables

A concise CTIPH AI-use statement implemented in active CTIPH D2L course shells.

One AI-use disclosure and verification question for a selected IPE worksheet, reflection, or post-event item.

An internal human-review checklist for AI-supported student- or facilitator-facing materials.

Documented review from at least one named faculty member, liaison, or IPE collaborator.

A refined workflow that can be extended to other IPE activities when capacity permits.

## Current University References

University of Arizona AI Tools & Data Use Guide: https://responsibleai.arizona.edu/ai-tools-guide

University of Arizona AI Guidelines & Principles: https://responsibleai.arizona.edu/ai-arizona/ai-guidelines-principles